## Sheet1
ID | Task | Category | Priority | Status | Assigned To | Due Date | Dependencies | Detailed Description | Impact | Comments
1 | Convert MRI data to Point Cloud format | Data Processing | High | Not Started | Team A | 2025-02-01 | None | Develop a module to convert MRI data in .nii format to 3D Point Cloud in .ply format. | Critical for foundational data generation for the system. | Initiate collaboration with data conversion experts.
2 | Integrate ARCore for camera scan data processing | Integration | High | In Progress | Team B | 2025-02-05 | Task 1 | Integrate Google's ARCore for processing camera scans into Point Cloud format. | Essential for capturing and integrating patient scan data. | Test integration with multiple camera systems.
3 | Optimize Point Cloud data through Simplification Module | Optimization | Medium | Not Started | Team A | 2025-02-10 | Task 2 | Simplify raw Point Cloud data to enhance system performance and reduce complexity. | Improves responsiveness and usability of the visualization system. | Ensure no critical data loss during simplification.
4 | Align MRI and camera data using Registration Module | Alignment | High | In Progress | Team C | 2025-02-15 | Task 3 | Register and align data from MRI and camera systems for unified visualization. | Ensures accuracy and reliability in aligning real and virtual data. | Test registration accuracy with sample datasets.
5 | Visualize 3D models with AR/VR technology | Visualization | Medium | Not Started | Team B | 2025-02-20 | Task 4 | Develop AR/VR interfaces to render final registered 3D models. | Provides an intuitive and immersive interface for surgeons. | Validate rendering on both AR glasses and monitors.
6 | Ensure compliance with patient data security standards | Security | High | Not Started | Team D | 2025-02-25 | None | Implement encryption and secure communication protocols for patient data. | Mandatory for maintaining patient trust and meeting compliance standards. | Perform security audits for compliance validation.
7 | Develop real-time synchronization for surgical guidance | Performance | High | Not Started | Team C | 2025-02-28 | Task 5 | Ensure the system provides precise, real-time updates with minimal latency. | Enables precise and efficient surgical navigation. | Conduct latency tests with sample surgical scenarios.
8 | Conduct initial testing for MRI data conversion module | Testing | Medium | Not Started | Team A | 2025-01-20 | Task 1 | Perform basic tests to ensure correct data conversion from .nii to .ply format. | Ensures conversion reliability before further processing. | Set up a testing environment with sample MRI datasets.
9 | Document ARCore integration process | Documentation | Low | In Progress | Team B | 2025-01-22 | Task 2 | Create step-by-step documentation of ARCore setup and integration. | Improves knowledge transfer and helps new team members onboard. | Use screenshots and clear instructions for the document.
10 | Optimize surface extraction algorithm for 3D models | Optimization | High | Not Started | Team A | 2025-01-25 | Task 3 | Refine and optimize the surface extraction process for better performance. | Enhances quality and accuracy of 3D surface models. | Profile the algorithm and identify bottlenecks.
11 | Run end-to-end testing for synchronization module | Testing | High | In Progress | Team C | 2025-01-30 | Task 5 | Run integrated tests to validate synchronization accuracy. | Validates the synchronization module for real-world use. | Test with different MRI datasets and AR/VR devices.
12 | Develop a user manual for surgeons | Documentation | Low | Not Started | Team D | 2025-01-28 | Task 5 | Create a detailed user manual with clear instructions for system usage. | Improves usability and reduces learning curve for new users. | Use visuals and diagrams to simplify instructions.
13 | Implement error handling for MRI module | Error Handling | High | Not Started | Team A | 2025-02-03 | Task 1 | Add robust error detection and handling mechanisms for corrupted MRI files. | Prevents data processing disruptions caused by invalid inputs. | Test handling with various sample datasets.
14 | Optimize AR/VR rendering pipeline | Optimization | High | In Progress | Team B | 2025-02-08 | Task 4 | Enhance the rendering pipeline to ensure smooth performance in AR/VR systems. | Guarantees high-quality visualization during surgeries. | Collaborate with AR/VR experts to profile performance.
15 | Set up a demo environment for stakeholder feedback | Testing | Medium | Not Started | Team D | 2025-02-12 | Task 8 | Prepare a demo version of the system for review by stakeholders. | Gathers insights to refine and improve the system. | Focus on showcasing key features to stakeholders.
16 | Conduct usability testing with healthcare professionals | User Testing | High | Not Started | Team C | 2025-02-18 | Task 8 | Gather feedback on system usability through hands-on testing sessions. | Validates the system's effectiveness and user-friendliness. | Recruit healthcare professionals for realistic testing scenarios.
17 | Verify compliance with HIPAA and GDPR standards | Compliance | High | Not Started | Team D | 2025-02-22 | Task 6 | Ensure data handling and storage comply with international regulations. | Builds trust and ensures legal compliance for deployment. | Perform a detailed review of security and compliance policies.